## Sheet1
|  | 0 | 1.1 | 1.2 | 1.3 | 1.4 | 1.5 | 1.6 | 1.7 | 1.8 | 1.9 | 1.1 | 2.1 | 2.2 | 2.3 | 2.4 | 2.5 | 2.6 | 2.7 | xmas 1 | xmas 2 | 2.8 | 2.9 | 2.1 | spring | 3.1 | 3.2 | 3.3 | 3.4 | 3.5 | 3.6 | 3.7 | 3.8 | 3.9 | 3.1
Item | Level | Summer | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11
Mission | 1 | x
Determine Mission | 2 | x
Determine Mission Objective | 3 | x
Determine Mission Constraints | 3 | x
Write Mission Statement | 3 | x
Systems Engineering | 1 | x | bar: 2021-08-30 to 2021-09-13
System Description | 2 | x
Interaction Between Spacecraft | 3 | x
Duty Cycles and Lifespan | 3 | x
Derive Relevant Requirements | 3 | x
Communication | 2 | bar: 2021-09-06 to 2021-09-13
Establish Baseline Link Budget | 3 | bar: 2021-09-06 to 2021-09-13
Formulate Budget as Function of Range | 3 | bar: 2021-09-06 to 2021-09-13
ADCS | 2 | bar: 2021-08-30 to 2021-09-06
Pointing Accuracy and Stability | 3 | bar: 2021-08-30 to 2021-09-06
Error Propapagation | 3 | bar: 2021-08-30 to 2021-09-06
CPU | 2 | bar: 2021-08-30
Establish Available Computing Power | 3 | bar: 2021-08-30
Judge Effect of Limited CPU Power | 3 | bar: 2021-08-30
Asteroid Population Modelling | 1 | bar: 2021-09-06 to 2021-09-13
Collect Models | 2 | bar: 2021-09-06 to 2021-09-13
ESA NEOPOP Model | 3 | bar: 2021-09-06
NEOWISE model | 3 | bar: 2021-09-13
NASA/JPL | 3 | bar: 2021-09-06
Implement Models | 2 | bar: 2021-09-06 to 2021-09-13
Generation of Asteroids | 3 | bar: 2021-09-06
Orbital Mechanics and Coordinates | 3 | bar: 2021-09-06
Verify Correct Implementation | 3 | bar: 2021-09-13
Storage of Models | 3 | bar: 2021-09-13
Survey modelling | 1 | x | bar: 2021-08-30 to 2021-09-20
Observation Model | 2 | x | bar: 2021-08-30 to 2021-09-13
Absolute to Apparent Magnitude | 3 | x
Modelling of PSF effects | 3 | x
Target Signal Calculation | 3 | x | bar: 2021-08-30 to 2021-09-13
Verify Correct Implementation | 3 | bar: 2021-09-06 to 2021-09-13
Noise and Background | 2 | x | bar: 2021-08-30 to 2021-09-20
Obtain Models for VIS and IR Background | 3 | x | bar: 2021-08-30 to 2021-09-13
Set up Tabulation and Interpolation | 3 | bar: 2021-09-06 to 2021-09-13
Background SNR Calculation | 3 | bar: 2021-09-06 to 2021-09-13
Verify Correct Implementation | 3 | bar: 2021-09-13 to 2021-09-20
Search Strategy | 2 | bar: 2021-09-20
Determine if Asteroid is in FOV | 3 | bar: 2021-09-13 to 2021-09-20
Define Search Area and Flexibility | 3 | bar: 2021-09-13 to 2021-09-20
Determine Cadence and Effects | 3 | bar: 2021-09-13 to 2021-09-20
Implement Search Strategy | 3 | bar: 2021-09-20
Optimization | 1 | bar: 2021-09-06 to 2021-10-11
Variables/Constraints | 2 | bar: 2021-09-06 to 2021-09-13
Determine Design Variables | 3 | bar: 2021-09-06 to 2021-09-13
Determine Optimizer Constraints | 3 | bar: 2021-09-06 to 2021-09-13
Formulation of the Variables | 3 | bar: 2021-09-06 to 2021-09-13
Optimizer | 2 | bar: 2021-09-06 to 2021-10-11
Determine Objective Function | 3 | bar: 2021-09-06 to 2021-09-13
Gather Optimization Methods | 3 | bar: 2021-09-13 to 2021-09-27
Trade-off Optimizers | 3 | bar: 2021-09-27 to 2021-10-11
Implement Optimization | 3 | bar: 2021-10-04 to 2021-10-11
Research | 1
Exploratory Research | 2 | bar: 2021-09-20 to 2021-10-11
Simulate 1-to-1 Relations Variables | 3 | bar: 2021-09-20 to 2021-10-04
Examine 1-to-1 Relations | 3 | bar: 2021-09-27 to 2021-10-11
Validate Relations | 3 | bar: 2021-10-04 to 2021-10-11
Examine Sensitivity and Variance | 3 | bar: 2021-10-04 to 2021-10-11
Decide Focus of Detailed Research | 3 | bar: 2021-10-11
Detailed Research | 2 | bar: 2021-10-11 to 2021-11-08
Scale up Computing Resources | 3 | bar: 2021-10-11 to 2021-10-18
Simulate Detailed Research Models | 3 | bar: 2021-10-11 to 2021-11-01
Examine Results Detailed Research | 3 | bar: 2021-10-25 to 2021-11-08
Follow-up Research | 2 | bar: 2021-11-08 to 2021-12-06
Perform Final Research | 3 | bar: 2021-11-08 to 2021-11-22
Examine Sensivity and Variance | 3 | bar: 2021-11-22 to 2021-12-06
Fitting and Statistical Analysis | 3 | bar: 2021-11-29 to 2021-12-06
Find Best Solutions | 3 | bar: 2021-11-22 to 2021-12-06
Analysis | 1 | bar: 2021-11-29 to 2021-12-20; 2022-01-10 to 2022-01-24
Analyse Results | 2 | bar: 2021-11-29 to 2021-12-20; 2022-01-10 to 2022-01-17
Draw Conclusions from Best Solutions | 3 | bar: 2021-11-29 to 2021-12-13
Analyse Sensitivity to Design Variables | 3 | bar: 2021-11-29 to 2021-12-13
Validate Population Model | 3 | bar: 2021-12-06 to 2021-12-20
Check Optimizer Generalization | 3 | bar: 2021-12-13 to 2021-12-20; 2022-01-10
Compare Results | 2 | bar: 2021-12-06 to 2021-12-20; 2022-01-10 to 2022-01-17
Compare Results in Own Work | 3 | bar: 2021-12-06 to 2021-12-20
Compare Results with Literature | 3 | bar: 2021-12-06 to 2021-12-13; 2022-01-10 to 2022-01-17
Conclude Things | 3 | bar: 2021-12-20; 2022-01-10 to 2022-01-17
Reporting | 1 | bar: 2021-09-06 to 2021-12-20; 2022-01-10 to 2022-01-24; 2022-02-07 to 2022-02-14
Intro/Conclusion/Abstract | 2 | bar: 2022-01-17 to 2022-01-24
Literature Review | 2 | bar: 2021-09-06 to 2021-09-20
Problem and Mission | 2 | bar: 2021-09-13 to 2021-10-04
Systems Engineering | 2 | bar: 2021-09-20 to 2021-10-04
Methodology | 2 | bar: 2021-09-27 to 2021-11-29
Population Modelling | 3 | bar: 2021-10-11 to 2021-11-01
Observation Modelling | 3 | bar: 2021-10-25 to 2021-11-29
Optimization | 3 | bar: 2021-11-08 to 2021-11-29
Results | 2 | bar: 2021-11-08 to 2021-12-20
Discussion | 2 | bar: 2021-12-06 to 2021-12-20; 2022-01-10 to 2022-01-17
Verification and Validation | 2 | bar: 2021-12-06 to 2021-12-20; 2022-01-10 to 2022-01-17
Drafting / improvement | 2 | bar: 2022-01-24; 2022-02-07 to 2022-02-14
Presentation | 1 | bar: 2022-02-21 to 2022-02-28
Presentation | 2 | bar: 2022-02-21 to 2022-02-28
Prepare Presentation | 3 | bar: 2022-02-21
Boom Rook | 3 | bar: 2022-02-21
Give Presentation | 3 | bar: 2022-02-28
Sign Paper | 3 | bar: 2022-02-28
Note on N2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mid-Term?
Note on Y2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Greenlight?
Note on AD2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Graduation?
Note on G46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Considered outside scope of this thesis. Definitely interesting for follow-up work!
Note on A58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is mainly linear / iterative work
Note on A74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is more non-linear. Hence the large number of selected squares